## Slide 1: CAPI and Tourism statistics: Progress to date
Prepared by Mairead Griffin

## Slide 2: Background to CAPI
Plans still in place for migration to CAPI
Benefits of CAPI:
  Better estimates
  Reduction in time lag between data collection and publication
  Ultimate aim: more frequent, timely and detailed data
  Aim to ‘future proof’ the methodology
  Warning: Break in series
Detailed internal report prepared for senior management (SMC) highlighting the cost/benefits of CAPI

## Slide 3: Background to CAPI (cont.)
Presentation on report findings made to SMC Dec 2014
Accepted by SMC that CAPI should be a priority
Lots of other areas all competing for limited resources
Accepted by SMC that the resources should be allocated to CAPI, but timing crucial
Sanction granted in mid February to go ahead with developing CAPI application but no commitment yet in relation to the additional staff required to implement it

## Slide 4: Progress to Date
Visits made to ONS and Madrid to review their CAPI systems and operations
Different operating systems used by both
Decision still to be finalized in relation to which system will be use by CSO
Technical specifications finalized and ready for development by IT once operating platform has been decided upon
To minimize disruption to users caused by break in series, will simultaneously introduce a revised sampling and grossing methodology

## Slide 5: User Input
Want to ‘future proof’ our methodology
Input from users very welcome – limited time
Initial discussions with some users on their needs
Want to hear from others
Initial priority = migrate current questionnaires

## Slide 6: Where we go from here – remainder of 2014
Lot to do this year
Finalize what platform to use for CAPI
Buy in the software or develop it internally?
Focus will be on building and testing
Aim to have prototype developed and in-house testing completed by end of year

## Slide 7: Where we go from here - remainder of 2014 (cont.)
Finalize our grossing methodology
Finalize external user requirements and incorporate them into the CAPI specifications
Review location of PCI interviewing at air and sea ports
Commence negotiations with interviewers/union representatives about implications of CAPI on their work
Working under the assumption that sanction will be received for the extra interviewers

## Slide 8: Where we go from here – 2015 onwards
2015 very busy
Early 2015: focus = on site testing of CAPI & finalizing CAPI infrastructure and software
Mid 2015 – finalize new methodologies (i.e. grossing/sampling etc.)
After Qtr 2 2015, more vague due to unknown resources
Subject to required enumerators being deployed:
  Q3 & Q4 – parallel runs and testing
  Final sign off on CAPI development
  Ready for going ‘live’ with CAPI by Q1 or Q2 2016.
Caution: Like all best laid plans – things may not go according to schedule

## Slide 9: Any Questions?
Thank you!